## Traceability Matrix
Test Case ID | Software Requirement ID | Functional Requirement ID | Requirement Description | Test Scenario | Test Data/Input | Expected Outcome | Actual Outcome | Status | Pass/Fail | Comments | Tester
TC-01 | SR-01 | SF-01, SF-02 | Quickly add assignments | Add a new assignment with all required information | Title, course, due date, priority, notes | The assignment is successfully added to the incomplete assignment list. | The assignment is successfully added to the incomplete assignment list. | Complete | Pass | May need to improve the interface of add assignment | Ziran Ren
TC-02 | SR-02 | SF-03, SF-04, SF-05 | Organize assignments in checklist | View assignments and mark one as completed | Existing assignment | The selected assignment moves to the completed list. | The selected assignment moves to the completed list. And also can delete assignments | Complete | Pass
TC-03 | SR-03 | SF-11 | Assignment deadline reminders | Create assignment reminder notification | Assignment with future due date | The system sends a notification before the due date. | The system show assigment due tomorrow | In progress
TC-04 | SR-04 | SF-04, SF-05 | Mark assignments as completed | Complete an assignment | Select incomplete assignment | The assignment status changes to completed. | The assignment status changes to completed. | Complete | Pass
TC-05 | SR-05 | SF-08, SF-10 | Reward/points system | Complete assignment to earn points | Completed assignment | Points are added to the user’s total points balance. | Points are added to the user’s total points balance. Each complete assignment worth 10 point, each overdue assignment worth -5 point | Complete | Pass | May need to adjust points earn from assignment (depend on hour expected of assignment)
TC-06 | SR-06 | SF-08, SF-10 | Redeem rewards from points | Redeem earned points | Available reward and sufficient points | The reward is redeemed and points are deducted correctly. | Can't redeemed reward. And Point can be negative | In progress | Fail | Need to complete
TC-07 | SR-07 | SF-01, SF-03, SF-12 | Simple and non-distracting system | Navigate through the application interface | Normal application usage | The interface remains simple, responsive, and easy to use. | There are still many interface can improve | In progress | Fail
TC-08 | SR-08 | SF-02, SF-12 | Add notes to assignments | Add notes to an assignment | Assignment notes/description | Notes are saved and displayed with the assignment details. | Notes are saved and displayed with the assignment details. | In progress | Pass | Interface of detal may need to adjust
TC-09 | SR-09 | SF-03, SF-05 | Separate completed and incomplete assignments | View completed and incomplete assignments separately | Assignments with different statuses | Assignments are displayed in separate sections correctly. | Assignments are displayed in separate sections correctly (include Incomplete Assignments and Completed Assignments) | Complete | Pass
TC-10 | SR-10 | SF-02, SF-07 | Prioritize assignments | Sort assignments by due date and priority | Assignments with different due dates and priorities | Assignments are sorted correctly based on selected criteria. | Assignments are sorted correctly based on selected criteria (due date or Priority) | Complete | Pass